## Slide 1
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved

## Slide 2
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Meeting Plan
G
Gotcha
Timeline
Gantt
  Raspberry Pi
  Server
  Tests
  Documents
  Admin application
  Rider application
Issues
Marathon Goals

## Slide 3
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Timeline
G
Gotcha
15.06 | 08.06 | 04.05 | 20.4 | 07.03
Iteration 3 | Poster | Iteration 2 | Marathon | Today Meeting

## Slide 4
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Raspberry Pi
G
Gotcha
15.06 | 08.06 | 04.05 | 20.4 | 07.03 | 
 |  |  |  | Done | Configuration
 |  |  |  | Done | Interfaces & Adapters
 |  |  |  | Done | Detection Models
 |  |  | Tom |  | Camera Module
 |  |  | Tom |  | GPS Module
 |  |  | Tom |  | Communication Module
 |  | Team (TBA) |  |  | Deployment

## Slide 5
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Server
G
Gotcha
15.06 | 08.06 | 04.05 | 20.4 | 07.03 | 
 |  |  |  | Done | Configuration
 |  |  | Sasha |  | User API
 |  |  | Amit |  | Admin API
 |  | Amit |  |  | Programmer API
 |  | Sasha |  |  | Database
 |  |  | Tom |  | Google maps
 | Team (TBA) |  |  |  | Deployment

## Slide 6
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Tests
G
Gotcha
15.06 | 08.06 | 04.05 | 20.4 | 07.03 | 
100% | 100% | 70% | Implement | Design | Unit
100% | 100% | 50% | Implement | Design | Integration
100% | 100% | 50% | Implement | Design | Stress
100% | 100% | Implement | Implement | Design | GUI manual tests
100% | 70% | Implement | Design | Design | Acceptance

## Slide 7
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Client
G
Gotcha
Admin windows
15.06 | 08.06 | 04.05 | 20.4 | 07.03 | 
 |  |  |  | Done | Login Window
 |  |  |  | Done | Home Window
 |  |  |  | Done | Users Window
 |  |  |  | Done | Admins Window
 |  |  |  | Done | Advertisements Window
 |  |  |  | Done | Questions Window
 |  |  | Amit |  | Hazards Window
 |  |  | Amit |  | Rides Window
 |  |  | Amit |  | Statistics Window
 |  |  | Amit |  | System settings Window
Amit |  |  |  |  | Improve design

## Slide 8
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Client
G
Gotcha
Rider windows
15.06 | 08.06 | 04.05 | 20.4 | 07.03 | 
 |  |  |  | Done | Login Window
 |  |  |  | Done | Change Password Window
 |  |  |  | Done | Reset Password Window
 |  |  | Tom |  | Register Window
 |  |  | Tom |  | Profile Window
 |  |  | Tom |  | User Rides Window
 |  |  | Tom |  | Ride Information Window
 |  |  | Tom |  | Announcements Window
 |  |  | Tom |  | Messages Window
 |  |  | Tom |  | Select Route Window
 |  |  | Tom |  | Ride Map Window
 |  |  | Tom |  | Active Ride Window
 |  |  | Tom |  | Home Window

## Slide 9
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Documents
G
Gotcha
15.06 | 08.06 | 04.05 | 20.4 | 07.03 | 
 |  |  |  | Sasha | Tests plan
 | V3 - Amit | V3 Draft | V2 - Amit | V2 Draft | ARD
V3 - Tom | V3 Draft | V2 - Tom | V2 Draft |  | ADD
V3 – Amit | V3 Draft | V2 - Amit | V2 Draft |  | Demo
 | Sasha | Draft |  |  | User Guideline
 | Amit | Draft |  |  | Admin Guideline
 | Amit | Draft |  |  | Programmer Guideline
 |  | Tom | Draft |  | Tests report (EXCEL)
 |  |  |  | Done | Presentation
 |  |  |  | Done | Video
TBA | Draft |  |  |  | Website (Q & A)

## Slide 10
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Issues
G
Gotcha
Design acceptance tests
Poster day
GUI manual tests / cypress

## Slide 11
Confidential and Proprietary. Copyright (c) by Gotcha. All Rights Reserved
Marathon Goals
G
Gotcha
Tests:
Acceptance tests design
Implement all tests
Tests report draft
Raspberry Pi:
RP – camera, GPS, communication
Improve detection model + define required errors
Documents:
ARD
ADD Draft V2
Demo Draft V2
Client:
Finish Rider windows
Finish Admin windows
Server:
User API
Admin API